## ErrorsTest3
Path | Task | WesID or Course ID | Expected Result | Actual Result | Exact wording of error message, if one appears | Resolution

## testing3
Task | Menu | Path |  | Comments | Tester | Date | WesID/Course/Class Created | Use this Data
Add person | Campus Community | Personal Information | Add/Update | Hispanic ethnicity | User1 | 2017-04-25 | emplid | Test Student 1
Add person | Campus Community | Personal Information | Add/Update | International student | User1 | 2017-04-25 | emplid | Test Student 2
Add person | Campus Community | Personal Information | Add/Update | Home address | User1 | 2017-04-25 | emplid | Test Student 3
Add person | Campus Community | Personal Information | Add/Update | Business Address | User1 | 2017-04-25 | emplid | Test Student 4
Set up terms - 1179 | Set Up SACR | Foundation Tables | Term Setup > Term/Session Table | GLSP | User1 | 2017-04-25 | IM1, 1176 updated
Set up terms - 1180 | Set Up SACR | Foundation Tables | Term Setup > Term/Session Table | UGRD Winter | User1 | 2017-04-25 | Done | Set up at least through 1199
Set up terms - 1177 | Set Up SACR | Foundation Tables | Term Setup > Term/Session Table | ICPP MA | User1 | 2017-04-25 | Done | Set up at least through 1199
Set up terms - 1177 | Set Up SACR | Foundation Tables | Term Setup > Term/Session Table | ICPP CERT | User1 | 2017-04-25 | n/a - Discontinued | Set up at least through 1199
Set up Academic Calendar - 1179 | Set Up SACR | Foundation Tables | Term Setup > Academic Calendar | GLSP | User1 | 2017-04-25 | IM1, 1176 updated | Changed 1176 1171
Set up Academic Calendar - 1180 | Set Up SACR | Foundation Tables | Term Setup > Academic Calendar | UGRD Winter | User1 | 2017-04-25 | Done | Set up at least through 1199
Set up Academic Calendar -1177 | Set Up SACR | Foundation Tables | Term Setup > Academic Calendar | ICPP MA | User1 | 2017-04-25 | Done | Set up at least through 1199
Set up Academic Calendar - 1177 | Set Up SACR | Foundation Tables | Term Setup > Academic Calendar | ICPP CERT | User1 | 2017-04-25 | n/a - Discontinued | Set up at least through 1199
Create Courses - 1177 | Curriculum Management | Course Catalog | Course Catalog | ICPP MA | User1 | 2017-04-25 | emplid, class 1002 1177 | ICPP559 Field Practicum
Create Courses - 1177 | Curriculum Management | Course Catalog | Course Catalog | ICPP CERT | User1 | 2017-04-25 | n/a - Discontinued | ICPP510 Considering Site
Set up GLS Self Service | See Documentation - multiple steps |  |  |  | User1 | 2017-04-25 | Done
Add person | Campus Community | Personal Information | Health Information | Add Immunizations | User2 | 2017-04-26 |  | EMPLID, Name
Add person | Campus Community | Personal Information | Identification | Add Slate ID | User2 | 2017-04-26 |  | EMPLID, Name
Add person | Campus Community | Personal Information | Biographical > Work Experience | Add work data | User2 | 2017-04-26 |  | EMPLID, Name
Add Service Indicators | Campus Community | Service Indicators (Students) |  | Add all GLS and GLI SI | User2 | 2017-04-26 |  | EMPLID, Name
Committee updates | Campus Community | Committees | Manage Committees | Add member | User1 | 2017-04-26 |  | EMPLID, Name
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/GLNON/GL_PREMATR | User2 | 2017-04-26 | emplid | Test Student 1
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/GLNON/PREMATR/SFAC | User2 | 2017-04-26 | emplid | Test Student 2
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/GLNON/PREMATR/GMATS | User2 | 2017-04-26 | emplid | Test Student 3
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/GLNON/INTF/Zwrite | User2 | 2017-04-26 | emplid | Test Student 4
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/GLNON/INTF/SFAC | User2 | 2017-04-26 |  | EMPLID, Name
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/GLNON/INTF/GMATS | User2 | 2017-04-26 |  | EMPLID, Name
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MALS/ARTS | User2 | 2017-04-26 |  | EMPLID, Name
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MALS/HUMS/ZWRITE | User2 | 2017-04-26 |  | EMPLID, Name
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MALS/MTHS | User2 | 2017-04-26 |  | EMPLID, Name
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MALS/SOCS/SFAC | User2 | 2017-04-26 |  | EMPLID, Name
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MALS/SCIE/GMATS | User2 | 2017-04-26 |  | EMPLID, Name
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MPHIL/ARTS | User2 | 2017-04-26 |  | EMPLID, Name
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MPHIL/HUMS | User2 | 2017-04-26 |  | EMPLID, Name
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MPHIL/MTHS | User2 | 2017-04-26 |  | EMPLID, Name
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MPHIL/SOCS/SFAC | User2 | 2017-04-26 |  | EMPLID, Name
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MPHIL/SCIE/GMATS | User2 | 2017-04-26 |  | EMPLID, Name
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GRAD/ICPP/ICPP-MA | User2 | 2017-04-26 |  | EMPLID, Name
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | DCST/CERT/ICPP | User2 | 2017-04-26 |  | EMPLID, Name
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | UGRD/UGNON/VSCH | User2 | 2017-04-26 |  | EMPLID, Name
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | UGRD/UGNON/HSCH | User2 | 2017-04-26 |  | EMPLID, Name
Inactivate | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/GLNON/PREMATR | User2 | 2017-04-26 |  | EMPLID, Name
Inactivate | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/GLNON/PREMATR/SFAC | User2 | 2017-04-26 |  | EMPLID, Name
Inactivate | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/GLNON/PREMATR/GMATS | User2 | 2017-04-26 |  | EMPLID, Name
Inactivate | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/GLNON/INTF | User2 | 2017-04-26 |  | EMPLID, Name
Inactivate | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MALS/ARTS | User2 | 2017-04-26 |  | EMPLID, Name
Inactivate | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MALS/HUMS/GMATS | User2 | 2017-04-26 |  | EMPLID, Name
Inactivate | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MALS/MTHS | User2 | 2017-04-26 |  | EMPLID, Name
Inactivate | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MALS/SOCS/SFAC | User2 | 2017-04-26 |  | EMPLID, Name
Inactivate | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MALS/SCIE/SFAC | User2 | 2017-04-26 |  | EMPLID, Name
Inactivate | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MPHIL/HUMS | User2 | 2017-04-26 |  | EMPLID, Name
Leave | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MALS/ARTS | User2 | 2017-04-26 |  | EMPLID, Name
Change Plans | Records & Enrollment | Career & Program Information | Student Program/Plan | From GLNON to MALS | User2 | 2017-04-26 |  | EMPLID, Name
Change Plans | Records & Enrollment | Career & Program Information | Student Program/Plan | From GLNON to MPHil | User2 | 2017-04-26 |  | EMPLID, Name
Change Plans | Records & Enrollment | Career & Program Information | Student Program/Plan | From MALS to MPHIL | User2 | 2017-04-26 |  | EMPLID, Name
Graduate Students | Records & Enrollment | Career & Program Information | Student Program/Plan | MALS | User2 | 2017-04-26 |  | EMPLID, Name
Graduate Students | Records & Enrollment | Career & Program Information | Student Program/Plan | MPHIL | User2 | 2017-04-26 |  | EMPLID, Name
Graduate Students | Records & Enrollment | Career & Program Information | Student Program/Plan | ICPP/MA | User2 | 2017-04-26 |  | EMPLID, Name
Graduate Students | Records & Enrollment | Career & Program Information | Student Program/Plan | ICPP/CERT | User2 | 2017-04-26 |  | EMPLID, Name
Add student to group | Records & Enrollment | Career & Program Information | Student Groups | SFAC | User2 | 2017-04-26 | emplid | Test Student - User1 to give ID
Add student to group | Records & Enrollment | Career & Program Information | Student Groups | GLSR | User2 | 2017-04-26 | emplid | Test Student - User1 to give ID
Create Courses, 1179 | Curriculum Management | Course Catalog | Course Catalog | GLSP ARTS | User2 | 2017-04-26 |  | ARTS 617, ARTS Test, EMPLID, Name
Create Courses, 1179 | Curriculum Management | Course Catalog | Course Catalog | GLSP HUMS | User2 | 2017-04-26 |  | HUMS629, HUMS Test, EMPLID, Name
Create Courses, 1179 | Curriculum Management | Course Catalog | Course Catalog | GLSP MTHS | User2 | 2017-04-26 |  | MTHS686, MTHS Test, EMPLID, Name
Create Courses, 1179 | Curriculum Management | Course Catalog | Course Catalog | GLSP SCIE | User2 | 2017-04-26 |  | SCIE655 TESTSOCS, EMPLID, Name
Create Courses, 1179 | Curriculum Management | Course Catalog | Course Catalog | GLSP SOCS | User2 | 2017-04-26 |  | SOCS655 TESTSOCS, EMPLID, Name
Schedule Courses -1179 | Curriculum Management | Schedule of Classes | Schedule New Course | GLSP ARTS | User2 | 2017-04-26
Change class schedule - 1179 | Curriculum Management | Schedule of Classes | Maindaine Schedule of Classes | GLSP HUMS | User2 | 2017-04-26
Cross List Class -1179 | Curriculum Management | Combined Sections | Combined Sections Table | GLSP socs | User2 | 2017-04-26
Cross List Class - 1179 | Curriculum Management | Combined Sections | Combined Sections Table | GLSP SCIE | User2 | 2017-04-26
Change schedule of cross listed classes - 1179 | Curriculum Management | Schedule of Classes | Schedule Class Meetings | GLSP MTHS | User2 | 2017-04-26 |  | Changed to M- Th
Change schedule of cross listed classes - 1179 | Curriculum Management | Schedule of Classes | Schedule Class Meetings | GLSP SCIE | User2 | 2017-04-26
Test sfac access to Self Service | Self Service |  |  |  | User3 | 2017-04-27
Manually Term Activate Students - 1176 | Records & Enrollment | Student Term Information | Term Activate a Student | GLS | User2 | 2017-04-27 |  | EMPLID, Name
Manually Term Activate Students - 1177 | Records & Enrollment | Student Term Information | Term Activate a Student | ICPP/MA | User1 | 2017-04-27 | Done | EMPLID, Name
Manually Term Activate Students - 1177 | Records & Enrollment | Student Term Information | Term Activate a Student | ICPP/CERT | User1 | 2017-04-27 | Done | EMPLID, Name
Manually Term Activate Students -1176 | Records & Enrollment | Student Term Information | Term Activate a Student | Summer/SUMR | User2 | 2017-04-27 |  | EMPLID, Name
Manually register students | Records & Enrollment | Enroll Students | Enrollment Request | GLS - vanilla -3 | User2 | 2017-04-28 |  | EMPLID, Name
Manually register students | Records & Enrollment | Enroll Students | Enrollment Request | GLS GMATS - 3 | User2 | 2017-04-28 |  | EMPLID, Name
Manually register students | Records & Enrollment | Enroll Students | Enrollment Request | GLS SFAC - 3 | User2 | 2017-04-28 |  | EMPLID, Name
Manually register students | Records & Enrollment | Enroll Students | Enrollment Request | GLS Audit - 3 | User2 | 2017-04-28 |  | EMPLID, Name
Manually register students | Records & Enrollment | Enroll Students | Enrollment Request | ICPP MA | User1 | 2017-04-28 | Done | EMPLID, Name
Manually register students | Records & Enrollment | Enroll Students | Enrollment Request | ICPP CERT | User1 | 2017-04-28 | Done | EMPLID, Name
Manually drop students | Records & Enrollment | Enroll Students | Enrollment Request | GLS - vanilla - 1 | User1 - Self Service | 2017-04-28 | Done | EMPLID, Name
Manually drop students | Records & Enrollment | Enroll Students | Enrollment Request | GLS GMATS - 1 | User2 | 2017-04-28 |  | EMPLID, Name
Manually drop students | Records & Enrollment | Enroll Students | Enrollment Request | GLS SFAC - 1 | User2 | 2017-04-28 |  | EMPLID, Name
Manually drop students | Records & Enrollment | Enroll Students | Enrollment Request | GLS Audit - 1 | User2 | 2017-04-28 |  | EMPLID, Name
Manually drop students | Records & Enrollment | Enroll Students | Enrollment Request | ICPP MA - 1 | User1 | 2017-04-28 | Done | EMPLID, Name
Manually drop students | Records & Enrollment | Enroll Students | Enrollment Request | ICPP CERT - 1 | User1 | 2017-04-28 |  | n/a
Register through Self Service | Self Service |  |  | User3, User2, and User4 | User3, User2, User4 | 2017-04-28 |  | EMPLID, Name
Register through Self Service | Self Service |  |  | Get fake passwords GLS vanilla | User1 | 2017-04-28 | emplids | EMPLID, Name
Manually register students | Records & Enrollment | Enroll Students | Enrollment | UGRD SUMR - 3 | User2 | 2017-04-28 | emplids | EMPLID, Name
Manually drop students | Records & Enrollment | Enroll Students | Enrollment Request | UGRD SUMW - 1 | User2 | 2017-04-28 |  | EMPLID, Name
Tuition Calculation | Student Financials | Tuition Calculation |  | UGRD SUMR - 3 | User1 | 2017-05-01 | Done | EMPLID, Name
Tuition Calculation | Student Financials | Tuition Calculation |  | GLS - vanilla -1 | User1 | 2017-05-01 | Done | EMPLID, Name
Tuition Calculation | Student Financials | Tuition Calculation |  | GLS GMATS - 1 | User1 | 2017-05-01 | Done | EMPLID, Name
Tuition Calculation | Student Financials | Tuition Calculation |  | GLS SFAC - 1 | User1 | 2017-05-01 | Done | EMPLID, Name
Tuition Calculation | Student Financials | Tuition Calculation |  | GLS Audit - 1 | User1 | 2017-05-01 | Done | EMPLID, Name
Tuition Calculation | Student Financials | Tuition & Fees | Tuition Calc | GLSP Career | User1 | 2017-05-01 | Done | All
Post charges | Student Financials | Charges & Payments | Group Processing - all | GLS scholarships | User1 | 2017-05-01 | Done | EMPLID, Name
Create Grade Rosters - 1171 | Curriculum Management | Grading | Create Grade Rosters | GLS | User1 | 2017-05-02 | Done | All
Create Grade Rosters - 1167 | Curriculum Management | Grading | Create Grade Rosters | ICPP-MA | User1 | 2017-05-02 | done | ICPP590 Adv Topic CP
Create Grade Rosters - 1167 | Curriculum Management | Grading | Create Grade Rosters | ICPP-Cert | User1 | 2017-05-02 | Done | ICPP515 Ent Strategies
Post Grades - 1177 | Curriculum Management | Grading | Grade Post | GLS | User1 | 2017-05-02 | Done | Class
Post Grades - 1167 | Curriculum Management | Grading | Grade Post | ICPP-MA | User1 | 2017-05-02 | SCIE681 | Post
Post Grades - 1167 | Curriculum Management | Grading | Grade Post | ICPP-Cert | User1 | 2017-05-02 | HUMS639 | Partial post
Comm Gen Reg Confirm - 1177 | Campus Community | Communication | Process from documentation | UGRD SUM | User2 | 2017-05-03
Comm Gen Milestone MALS/MPHIL - 1171 | Campus Community | Communication | Process from documentation | GLS | User1 | 2017-05-03 | Done
Comm Gen GCW - 1171 | Campus Community | Communication | Process from documentation | GLS | User1 | 2017-05-03 | Done
Comm Gen Graduation - 1171 | Campus Community | Communication | Process from documentation | GLS | User1 | 2017-05-03 | Done
BIP Reporting - 1171 | Reporting Tools | BI Publisher | Schedule | GLSGCMLSTN | User3 | 2017-05-04
BIP Reporting - 1171 | Reporting Tools | BI Publisher | Schedule | GLSGRADMAIL | User3 | 2017-05-04
BIP Reporting - 1171 | Reporting Tools | BI Publisher | Schedule | GLS_DGR_AUD | User3 | 2017-05-04
BIP Reporting- 1171 | Reporting Tools | BI Publisher | Schedule | GLS_MILESTON | User3 | 2017-05-04
BIP Reporting - 1176 | Reporting Tools | BI Publisher | Schedule | INTERSESSIO | User2 | 2017-05-04
| Reporting Tools | Query |  | Run queries used frequently | All | 2017-05-04
Wait list and move off | [6 empty] | Class 1055, 1054, 1056, student 361430 w/l and added.

## Testing
Task | Menu | Path |  | Comments | Tester | Test due date 1 | WesID/Course/Class Created | Use this WesID | Results 1 | Results 2 | Results 3
Add person | Campus Community | Personal Information | Add/Update | Hispanic ethnicity | User2 | Tues, 2/28 | EMPLID | MALS/HUMS | Success | EMPLID
Add person | Campus Community | Personal Information | Add/Update | International student | User2 | Tues, 2/28 | EMPLID | MPHIL/SCIE | Success | EMPLID
Add person | Campus Community | Personal Information | Add/Update | Home address | User2 | Tues, 2/28 | EMPLID |  | Success | EMPLID
Add person | Campus Community | Personal Information | Add/Update | Business Address | User2 | Tues, 2/28 | EMPLID |  | Success | EMPLID
Add person | Campus Community | Personal Information | Health Information | Add Immunizations | User2 | Tues, 2/28 | EMPLID |  | Success | EMPLID
Add person | Campus Community | Personal Information | Identification | Add Slate ID | User2 | Tues, 2/28 | EMPLID |  | Success | EMPLID
Add person | Campus Community | Personal Information | Biographical > Work Experience | Add work data | User2 | Tues, 2/28 | EMPLID |  | Success | EMPLID
Add Service Indicators | Campus Community | Service Indicators (Students) |  | Add all GLS and GLI SI | User2 | Tues, 2/28 |  | EMPLID, NAME | Success - all added and released | EMPLID
Committee updates | Campus Community | Committees | Manage Committees | Add member | User1 | Tues, 2/28 |  | EMPLID, NAME | Success | EMPLID
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/GLNON/GL_PREMATR | User2 | Tues, 2/28 |  | EMPLID, NAME | Success - RADM | EMPLID
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/GLNON/PREMATR/SFAC | User2 | Tues, 2/28 |  | EMPLID, NAME | Success | EMPLID
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/GLNON/PREMATR/GMATS | User2 | Tues, 2/28 |  | EMPLID, NAME | Success
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/GLNON/INTF/Zwrite | User2 | Tues, 2/28 |  | EMPLID, NAME | Success
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/GLNON/INTF/SFAC | User2 | Tues, 2/28 |  | EMPLID, NAME | success
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/GLNON/INTF/GMATS | User2 | Tues, 2/28 |  | EMPLID, NAME | success | EMPLID
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MALS/ARTS | User2 | Tues, 2/28 |  | EMPLID, NAME | success
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MALS/HUMS/ZWRITE | User2 | Tues, 2/28 |  | EMPLID, NAME | Success | EMPLID
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MALS/MTHS | User2 | Tues, 2/28 |  | EMPLID, NAME | Success
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MALS/SOCS/SFAC | User2 | Tues, 2/28 |  | EMPLID, NAME | success
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MALS/SCIE/GMATS | User2 | Tues, 2/28 |  | EMPLID, NAME | success
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MPHIL/ARTS | User2 | Tues, 2/28 |  | EMPLID, NAME | success
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MPHIL/HUMS | User2 | Tues, 2/28 |  | EMPLID, NAME | success | EMPLID
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MPHIL/MTHS | User2 | Tues, 2/28 |  | EMPLID, NAME | success
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MPHIL/SOCS/SFAC | User2 | Tues, 2/28 |  | EMPLID, NAME | success
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MPHIL/SCIE/GMATS | User2 | Tues, 2/28 |  | EMPLID, NAME | Success
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | GRAD/ICPP/ICPP-MA | User2 | Tues, 2/28 |  | EMPLID, NAME | Success | EMPLID
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | DCST/CERT/ICPP | User2 | Tues, 2/28 |  | EMPLID, NAME | Success | Program discontinued
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | UGRD/UGNON/VSCH | User2 | Tues, 2/28 |  | EMPLID, NAME | Success
Set up careers | Records & Enrollment | Career & Program Information | Student Program/Plan | UGRD/UGNON/HSCH | User2 | Tues, 2/28 |  | EMPLID, NAME | Success
Inactivate | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/GLNON/PREMATR | User2 | Tues, 2/28 |  | EMPLID, NAME | Success - got warning when student was in class | Success, TC flag
Inactivate | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/GLNON/PREMATR/SFAC | User2 | Tues, 2/28 |  | EMPLID, NAME | already done
Inactivate | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/GLNON/PREMATR/GMATS | User2 | Tues, 2/28 |  | EMPLID, NAME | Success, correctly not pulled in Active Students
Inactivate | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/GLNON/INTF | User2 | Tues, 2/28 |  | EMPLID, NAME | Success, correctly not pulled in Active Students
Inactivate | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MALS/ARTS | User2 | Tues, 2/28 |  | EMPLID, NAME | Success, correctly not pulled in Active Students
Inactivate | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MALS/HUMS/GMATS | User2 | Tues, 2/28 |  | EMPLID, NAME | Success, correctly not pulled in Active Students
Inactivate | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MALS/MTHS | User2 | Tues, 2/28 |  | EMPLID, NAME | Success, correctly not pulled in Active Students
Inactivate | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MALS/SOCS/SFAC | User2 | Tues, 2/28 |  | EMPLID, NAME | Success
Inactivate | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MALS/SCIE/SFAC | User2 | Tues, 2/28 |  | EMPLID, NAME | Degree IR, error message | Degree IR, error message
Inactivate | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MPHIL/HUMS | User2 | Tues, 2/28 |  | EMPLID, NAME | success
Leave | Records & Enrollment | Career & Program Information | Student Program/Plan | GLSP/MALS/ARTS | User2 | Tues, 2/28 |  | EMPLID, NAME | Success
Change Plans | Records & Enrollment | Career & Program Information | Student Program/Plan | From GLNON to MALS | User2 | Tues, 2/28 |  | EMPLID, NAME | success
Change Plans | Records & Enrollment | Career & Program Information | Student Program/Plan | From GLNON to MPHil | User2 | Tues, 2/28 |  | EMPLID, NAME | success
Change Plans | Records & Enrollment | Career & Program Information | Student Program/Plan | From MALS to MPHIL | User2 | Tues, 2/28 |  | EMPLID, NAME | success | Error EMPLID
Graduate Students | Records & Enrollment | Career & Program Information | Student Program/Plan | MALS | User2 | Tues, 2/28 |  | EMPLID, NAME | Success | Success, EMPLID
Graduate Students | Records & Enrollment | Career & Program Information | Student Program/Plan | MPHIL | User2 | Tues, 2/28 |  | EMPLID, NAME | Success | Error EMPLID
Graduate Students | Records & Enrollment | Career & Program Information | Student Program/Plan | ICPP/MA | User2 | Tues, 2/28 |  | EMPLID, NAME | Hold
Graduate Students | Records & Enrollment | Career & Program Information | Student Program/Plan | ICPP/CERT | User2 | Tues, 2/28 |  | EMPLID, NAME | Hold
Add student to group | Records & Enrollment | Career & Program Information | Student Groups | SFAC | User2 | Tues, 2/28 | EMPLID | New GLS ID | GLSR | EMPLIDS
Add student to group | Records & Enrollment | Career & Program Information | Student Groups | GLSR | User2 | Tues, 2/28 | EMPLID | New GLS ID | SFAC | EMPLIDS
Set up terms - 1179 | Set Up SACR | Foundation Tables | Term Setup > Term/Session Table | GLSP | User1 | Tues, 2/28 |  | Changed 1176 1171 | success
Set up terms - 1180 | Set Up SACR | Foundation Tables | Term Setup > Term/Session Table | UGRD Winter | User1 | Tues, 2/28 |  | Set up at least through 1199 | Success
Set up terms - 1177 | Set Up SACR | Foundation Tables | Term Setup > Term/Session Table | ICPP MA | User1 | Tues, 2/28 |  | Set up at least through 1199 | Success
Set up terms - 1177 | Set Up SACR | Foundation Tables | Term Setup > Term/Session Table | ICPP CERT | User1 | Tues, 2/28 |  | Set up at least through 1199 | Success
Set up Academic Calendar - 1179 | Set Up SACR | Foundation Tables | Term Setup > Academic Calendar | GLSP | User1 | Tues, 2/28 |  | Changed 1176 1171 | Success | Changed GLS1176, 1171
Set up Academic Calendar - 1180 | Set Up SACR | Foundation Tables | Term Setup > Academic Calendar | UGRD Winter | User1 | Tues, 2/28 |  | Set up at least through 1199 | Success
Set up Academic Calendar -1177 | Set Up SACR | Foundation Tables | Term Setup > Academic Calendar | ICPP MA | User1 | Tues, 2/28 |  | Set up at least through 1199 | Success
Set up Academic Calendar - 1177 | Set Up SACR | Foundation Tables | Term Setup > Academic Calendar | ICPP CERT | User1 | Tues, 2/28 |  | Set up at least through 1199 | Success
Create Courses, 1179 | Curriculum Management | Course Catalog | Course Catalog | GLSP ARTS | User2 | Wed, 3/1 | EMPLID | ARTS 617, ARTS Test, EMPLID, NAME | success | EMPLID
Create Courses, 1179 | Curriculum Management | Course Catalog | Course Catalog | GLSP HUMS | User2 | Wed, 3/1 | EMPLID | HUMS629, HUMS Test, EMPLID, NAME | success
Create Courses, 1179 | Curriculum Management | Course Catalog | Course Catalog | GLSP MTHS | User2 | Wed, 3/1 | EMPLID | MTHS686, MTHS Test, EMPLID, NAME | success
Create Courses, 1179 | Curriculum Management | Course Catalog | Course Catalog | GLSP SCIE | User2 | Wed, 3/1 | EMPLID | SCIE655 TESTSOCS, EMPLID, NAME | success | EMPLID
Create Courses, 1179 | Curriculum Management | Course Catalog | Course Catalog | GLSP SOCS | User2 | Wed, 3/1 | EMPLID | SOCS655 TESTSOCS, EMPLID, NAME | success | EMPLID
Create Courses - 1177 | Curriculum Management | Course Catalog | Course Catalog | ICPP MA | User1 | Wed, 3/1 | EMPLID/1002 | ICPP585 Field Practicum | success
Create Courses - 1177 | Curriculum Management | Course Catalog | Course Catalog | ICPP CERT | User1 | Wed, 3/1 | EMPLID/1003 | ICPP510 Considering Site | success
Schedule Courses -1179 | Curriculum Management | Schedule of Classes | Schedule New Course | GLSP ARTS | User2 | Wed, 3/1 | 3317 |  | Success | 3364, 3365
Change class schedule - 1179 | Curriculum Management | Schedule of Classes | Maindaine Schedule of Classes | GLSP HUMS | User2 | Wed, 3/1 | 3318 |  | Success | 3364, 3365
Cross List Class -1179 | Curriculum Management | Combined Sections | Combined Sections Table | GLSP socs | User2 | Wed, 3/1 | 3320 |  | Success | 3364, 3365
Cross List Class - 1179 | Curriculum Management | Combined Sections | Combined Sections Table | GLSP SCIE | User2 | Wed, 3/1 | 3319 |  | Success | 3364, 3365
Change schedule of cross listed classes - 1179 | Curriculum Management | Schedule of Classes | Schedule Class Meetings | GLSP MTHS | User2 | Wed, 3/1 | 3321 | Changed to M- Th | Success
Change schedule of cross listed classes - 1179 | Curriculum Management | Schedule of Classes | Schedule Class Meetings | GLSP SCIE | User2 | Wed, 3/1 |  | Correct - cannot do in schedule new or maintain; changed in Schedule, SOCS changed | Success | 3364, 3365
Test sfac access to Self Service | Self Service |  |  | Tina, please try to register for 1176 in the afternoon | User2 | Wed, 3/1 |  | EMPLID, NAME | Success | Success, EMPLIDS
Set up GLS Self Service | See Documentation - multiple steps |  |  |  | User1 | Wed, 3/1 |  |  | Success | success
Manually Term Activate Students - 1176 | Records & Enrollment | Student Term Information | Term Activate a Student | GLS | User2 | Thurs, 3/2 |  | EMPLID, NAME | Success | EMPLID
Manually Term Activate Students - 1177 | Records & Enrollment | Student Term Information | Term Activate a Student | ICPP/MA | User1 | Thurs, 3/2 |  | EMPLID, NAME | Success | EMPLID
Manually Term Activate Students - 1177 | Records & Enrollment | Student Term Information | Term Activate a Student | ICPP/CERT | User1 | Thurs, 3/2 |  | EMPLID, NAME | Success | Discontinued
Manually Term Activate Students -1176 | Records & Enrollment | Student Term Information | Term Activate a Student | Summer/SUMR | User2 | Thurs, 3/2 |  | EMPLID, NAME | Success | EMPLID; rest already TA
Manually register students | Records & Enrollment | Enroll Students | Enrollment Request | GLS - vanilla -3 | User2 | Thurs, 3/2 | Assorted; | EMPLID, NAME | Success - errored on time conflict, did not stop for expired SI, blocked no apt, blocked SI | Success - errored on time conflict, did not stop for expired SI, blocked no apt, blocked SI
Manually register students | Records & Enrollment | Enroll Students | Enrollment Request | GLS GMATS - 3 | User2 | Thurs, 3/2 |  | EMPLID, NAME | Success | Success
Manually register students | Records & Enrollment | Enroll Students | Enrollment Request | GLS SFAC - 3 | User2 | Thurs, 3/2 |  | EMPLID, NAME | Success
Manually register students | Records & Enrollment | Enroll Students | Enrollment Request | GLS Audit - 3 | User2 | Thurs, 3/2 | 1034 | EMPLID, NAME | success | Success put student on waitlist for full course
Manually register students | Records & Enrollment | Enroll Students | Enrollment Request | ICPP MA | User1 | Thurs, 3/2 |  | EMPLID, NAME | Success
Manually register students | Records & Enrollment | Enroll Students | Enrollment Request | ICPP CERT | User1 | Thurs, 3/2 |  | EMPLID, NAME | Success
Manually drop students after MK OK | Records & Enrollment | Enroll Students | Enrollment Request | GLS - vanilla - 1 | User2 | Thurs, 3/2 |  | EMPLID, NAME | Success | EMPLID, error, w grade
Manually drop students after MK OK | Records & Enrollment | Enroll Students | Enrollment Request | GLS GMATS - 1 | User2 | Thurs, 3/2 | effective 3/14, | EMPLID, NAME | Success, grade = W | Grade = W
Manually drop students after MK OK | Records & Enrollment | Enroll Students | Enrollment Request | GLS SFAC - 1 | User2 | Thurs, 3/2 | effective 3/13 | EMPLID, NAME | Success
Manually drop students after MK OK | Records & Enrollment | Enroll Students | Enrollment Request | GLS Audit - 1 | User2 | Thurs, 3/2 |  | EMPLID, NAME | Error - effecctive 3/15, but rec'd W grade
Attempt to drop w/o grade | changed fully graded date | [6 empty] | EMPLID, NAME | Error - effecctive 3/15, but rec'd W grade
Change dwgp to 3/15 from blank'
Manually drop students | Records & Enrollment | Enroll Students | Enrollment Request | ICPP MA - 1 | User1 | Thurs, 3/2 |  | EMPLID, NAME | success
Manually drop students | Records & Enrollment | Enroll Students | Enrollment Request | ICPP CERT - 1 | User1 | Thurs, 3/2 |  | EMPLID, NAME | success | Discontinues
Register through Self Service | Self Service |  |  | Sarah-Jane, Tina, and Sam | Sarah-Jane, User2, Sam | Thurs, 3/2 |  | EMPLID, NAME | success | Success, EMPLIDS
Register through Self Service | Self Service |  |  | Get fake passwords GLS vanilla | User1 | Thurs, 3/2 |  | EMPLID, NAME |  | Done
Manually register students | Records & Enrollment | Enroll Students | Enrollment | UGRD SUMR - 3 | User2 | Thurs, 3/2 | 1015 | EMPLID, NAME | success | Success
Manually drop students after MK OK | Records & Enrollment | Enroll Students | Enrollment Request | UGRD SUMW - 1 | User2 | Thurs, 3/2 |  | EMPLID, NAME | success | Success
Tuition Calculation | Student Financials | Tuition Calculation |  | UGRD SUMR - 3 | User1 | Thurs, 3/2 |  | EMPLID, NAME | success | Success
Tuition Calculation | Student Financials | Tuition Calculation |  | GLS - vanilla -1 | User1 | Thurs, 3/2 |  | EMPLID, NAME | success | Success
Tuition Calculation | Student Financials | Tuition Calculation |  | GLS GMATS - 1 | User1 | Thurs, 3/2 |  | EMPLID, NAME | success | Success
Tuition Calculation | Student Financials | Tuition Calculation |  | GLS SFAC - 1 | User1 | Thurs, 3/2 |  | EMPLID, NAME | success
Tuition Calculation | Student Financials | Tuition Calculation |  | GLS Audit - 1 | User1 | Thurs, 3/2 |  | EMPLID, NAME | success
Tuition Calculation | Student Financials | Tuition & Fees | Tuition Calc | GLSP Career | User1 | Thurs, 3/2 |  | All | success
Post charges | Student Financials | Charges & Payments | Group Processing - all | GLS scholarships | User1 | Thurs, 3/2 |  | EMPLIDS | Success
Create Grade Rosters - 1171 | Curriculum Management | Grading | Create Grade Rosters | GLS | User1 | Thurs, 3/2 |  | HUMS623, NAME | RC=GLS1171TEST, grade rosters created | success all 1171
Create Grade Rosters - 1167 | Curriculum Management | Grading | Create Grade Rosters | ICPP-MA | User1 | Thurs, 3/2 |  | ICPP590 Adv Topic CP | Success
Create Grade Rosters - 1167 | Curriculum Management | Grading | Create Grade Rosters | ICPP-Cert | User1 | Thurs, 3/2 |  | ICPP515 Ent Strategies | Success
Post Grades - 1177 | Curriculum Management | Grading | Grade Post | GLS | User1 | 2017-03-08 |  | HUMS623, NAME | Success | Partial post success
Post Grades - 1167 | Curriculum Management | Grading | Grade Post | ICPP-MA | User1 | Thurs, 3/2 |  | Post | Success
Post Grades - 1167 | Curriculum Management | Grading | Grade Post | ICPP-Cert | User1 | Thurs, 3/2 |  | Partial post | Success
Comm Gen Reg Confirm - 1177 | Campus Community | Communication | Process from documentation | UGRD SUM | User2 | Thurs, 3/2 |  |  | success
Comm Gen Milestone MALS/MPHIL - 1171 | Campus Community | Communication | Process from documentation | GLS | User1 | Thurs, 3/2 |  |  | Errors in class tables - GCW issue | G1G Error in preview - did not email
Comm Gen GCW - 1171 | Campus Community | Communication | Process from documentation | GLS | User1 | Thurs, 3/2
Comm Gen Graduation - 1171 | Campus Community | Communication | Process from documentation | GLS | User1 | Thurs, 3/2
BIP Reporting - 1171 | Reporting Tools | BI Publisher | Schedule | GLSGCMLSTN | User1 | Thurs, 3/2
BIP Reporting - 1171 | Reporting Tools | BI Publisher | Schedule | GLSGRADMAIL | User1 | Thurs, 3/2
BIP Reporting - 1171 | Reporting Tools | BI Publisher | Schedule | GLS_DGR_AUD | User1 | Thurs, 3/2 |  |  | Success
BIP Reporting- 1171 | Reporting Tools | BI Publisher | Schedule | GLS_MILESTON | User1 | Thurs, 3/2
BIP Reporting - 1176 | Reporting Tools | BI Publisher | Schedule | INTERSESSIO | User2 | Thurs, 3/2 |  |  |  | Success
Waitlist | [7 empty] | EMPLID, NAME | success | Success
Test multiple enrl limit in combined section class | [6 empty] | 1032 | EMPLID, NAME | success | Success
Drop student from full class, attempt to add student to class with waitlist | [6 empty] | 1043 | EMPLID, NAME | Success - she was waitlisted | Success - She Was Waitlisted
move position, enroll from waitlist | [6 empty] | 1043 | EMPLID, NAME | Success - enrolled | Success - Enrolled
Change student email addresses to mgkelly@wesleyan to verify completion of comm gen | Campus Community | Add/Update
Verify comm gen went out | Query Mgr |  | WCSD_RPT_COMMGEN_RESULTS/RPT_COMM_GEN

## Errors Test 2
Path | Task | WesID or Course ID | Expected Result | Actual Result | Exact wording of error message, if one appears | Resolution
Records & Enrollment > Career & Program Info > Student Program Plan | Graduate Student | 274131, 417937 | Student awarded degree/GCW | error, but worked on student with no prior GLS degree 329190 | Remote programs SRPCDDRV failed with reason: GETCH-S-TPLAN (2, -1) DERIVED_CS.UPDT_DEGR_PB.FiledChange PCPC
Records & Enrollment > Enroll Students > Enrollment Request | Drop student after drop with penalty date | 338130, class 3359 | Student not permitted to drop | Past Drop with Penalty Date, system processed as within Drop w/Penalty and gave W | INC0048476
Campus Community > Communications > Communication Generation | G1G, milestone |  | Preview emails in outlook | CS recorded success, no emails rec'd | INC0049695

## Errors Test 1
Path | Task | WesID or Course ID | Expected Result | Actual Result | Exact wording of error message, if one appears | Resolution
Example: Records & Enrollment > Career & Program Information > Student Program/Plan | Inactivate student | 356179 | Add row with DISC/INAC | Box for Action Reason red, would not let me select INAC | ORAC:989098098090 this is a test message | Fixed 2/28/2017
Campus Community > Personal Information > Add/Update a person | Add new person | n/a | New WesID | Did not save | HMCR_FRAMEWORK.ServiceFramework.Utilities.ServiceManager.OnExecute Name:LocateService PCPC:1628 Statement:37 Called from:SCC_PERSON_SOA_CONSUMER.PersonServiceConsumer.SCC_PersBioConsumer.OnExecute Name:validatePersNID Statement:408 Called from:SCC_BIO_DEMO.GBL.SCC_PERS_NID_H.SaveEdit Statement:1 not found in the registry (18137,5) The PeopleCode program executed an Error statement, which has produced this message. | Cache cleared by ITS on server
Campus Community > Personal Information > Add/Update a person | Per GB request - no SSN |  |  |  | HMCR_FRAMEWORK.ServiceFramework.Utilities.ServiceManager.OnExecute Name:LocateService PCPC:1628 Statement:37 Called from:HCR_PERSON_SERVICES.Person.SetPerson_v1_0.implSetPerson.OnExecute Name:DoService Statement:34 Called {Success]from:HCR_PERSON_SERVICES.Person.AddPerson_v1_0.implAddPerson.OnExecute Name:DoService Statement:26 Called from:SCC_PERSON_SOA_CONSUMER.PersonServiceConsumer.SCC_PersBioConsumer.OnExecute Name:setData Statement:116 Called from:SCC_BIO_DEMO.GBL.SavePostChange Statement:4 not found | Cache cleared by ITS on server
Records & Enrollment > Career Program Info > Student Program/Plan | Graduate student | EMPLID | Degree updated |  | CCOBOL Program SRPCDDRV aborted (2,-1) DERIVED_CS.UPDT_DEGR_PB.FieldChange PCPC:1023 Statement:23
Curriculum Mgt > Schedule of Classes > Schedule New Course | Schedule Course in 1179 | EMPLID ARTS617 | Class scheduled M 6 pm | Error | COBOL Program SRPQUERC aborted (2,-1) FUNCLIB_SR.RESOURCE_NAME.FieldFormula Name:ResourceQueue PCPC:783 Statement:6 Called from:CLASS_TBL.CRSE_OFFER_NBR.SaveEdit Statement:33 | Fixed 3/7/2017
Records & Enrollment > Term Processing > Appointments > Appointment Table | Set up GLS enrollment apts for paying students for 1176 | n/a | Enrollment apt blocks saved 3/1/17 - 3/7/17 | Error message; seeing first day to enroll as last | Appointment end date is after last date to enroll (2017-02-28) (14600,763) | Still error 3/8/2017 | Security error, but found work around
https://cs90test-nocas.wesleyan.edu/psp/ps/?cmd=login&languageCd=ENG& | Log in as new student | EMPLID | Self Service menu | Authorization Error -- Contact your Security Administrator | https://cs90test-nocas.wesleyan.edu/psc/ps/EMPLOYEE/HRMS/s/WEBLIB_PTBR.ISCRIPT1.FieldFormula.IScript_StartPage | Still error 3/8/2017
Curriculum Mgt > Grading > Grade Roster | Partial Post grades | EMPLID HUMS639 1171 | Partial post | Error message. | COBOL Program SRPCGPRC aborted (2,-1) DERIVED_CS.GRD_RSTR_POST_PB.FieldChange PCPC:567 Statement:4 | Fixed 3/7/2017
|  |  | Comm Gen | class table error |  | MK to review
Reporting Tools > BI Publisher > Query Report Scheduler | Run BIP reports |  |  | Did not carry process name to process monitor | Called from:XPQRYRUN_WRK.QRYSCHEDULE.FieldChange Statement:7 Called from:PRCSRQSTDLG_WRK.LOADPRCSRQSTDLGPB.FieldFormula Name:LaunchProcessRequestDlg Statement:1329 The attribute specified is required for the ProcessRequest PeopleCode object class to be able to schedule the request appropriately. | There is an old ticket, INC0019387 that had the same situation with Connected Query. Ultimately, it required an addition (Process Group TLSALL) to a delivered Permission List in Security. I am putting the process into the Work notes.
Records & Enrollment > Enroll > Enrollment Request | Enrollment Request after withdrawal deadline |  | Not able to w/d | Student received W | EMPLIDS

## PT 1176 Course
Count of Descr
Meet times | Class Nbr | Total
..T.H.. 01:00PM-04:00PM | 1034 | 1
..T.H.. 01:00PM-04:00PM Total |  | 1
..T.H.. 06:30PM-09:30PM | 1032 | 1
| 1037 | 1
| 1042 | 1
| 1043 | 1
..T.H.. 06:30PM-09:30PM Total |  | 4
..T.H.. 09:00AM-12:00PM | 1038 | 1
..T.H.. 09:00AM-12:00PM Total |  | 1
.M.W... 01:00PM-04:00PM | 1035 | 1
.M.W... 01:00PM-04:00PM Total |  | 1
.M.W... 06:30PM-09:30PM | 1041 | 1
| 1044 | 1
| 1045 | 1
| 1048 | 1
| 1049 | 1
| 1050 | 1
| 1051 | 1
| 1052 | 1
| 1053 | 1
.M.W... 06:30PM-09:30PM Total |  | 9
.M.W... 09:00AM-12:00PM | 1036 | 1
| 1046 | 1
| 1047 | 1
.M.W... 09:00AM-12:00PM Total |  | 3
.MTWHF. 09:00AM-05:00PM | 1039 | 1
| 1040 | 1
.MTWHF. 09:00AM-05:00PM Total |  | 2
TBA | 1054 | 1
| 1055 | 1
| 1056 | 1
TBA Total |  | 3
Grand Total |  | 24

## 1176 Course
Info course cheat sheet & PR | 24
Term | Class Nbr | Subject | Catalog | Descr | Session | Start Date | End Date | Meet times | Facilty | ID | Instructor Name | Cap Enrl | Tot Enrl | Class Stat | Auto Enrol | Wait Cap | Preferred Email | Course ID | Comb Sect | Flat Amt | Fees Exist | Attr
1176 | 1032 | ARTS | 615 | Jazz Intersections: Rock, Soul | JA1 | 2017-06-26 | 2017-08-01 | ..T.H.. 06:30PM-09:30PM |  | EMPLID | Instructor Name | 18 | 2 | A | Y | 10 |  | 014841 | C | 0 | N | ZONL
1176 | 1043 | ARTS | 615W | Jazz Intersections: Rock, Soul | JA1 | 2017-06-26 | 2017-08-01 | ..T.H.. 06:30PM-09:30PM |  | EMPLID | Instructor Name | 3 | 0 | A | Y | 3 |  | 014841 | C | 0 | N | ZGWC, ZONL
1176 | 1034 | ARTS | 616 | Screenwriting: The Art of Visu | JA1 | 2017-06-26 | 2017-08-01 | ..T.H.. 01:00PM-04:00PM |  | EMPLID | Instructor Name | 18 | 0 | A | Y | 10 |  | 014842 |  | 0 | N | ZGWC
1176 | 1035 | ARTS | 644 | The Water-Based: Color Through | JA1 | 2017-06-26 | 2017-08-01 | .M.W... 01:00PM-04:00PM |  | EMPLID | Instructor Name | 18 | 0 | A | Y | 10 |  | 014843 |  | 0 | N
1176 | 1036 | HUMS | 609 | Narrative Trends and New Audie | JA1 | 2017-06-26 | 2017-08-01 | .M.W... 09:00AM-12:00PM |  | EMPLID | Instructor Name | 18 | 0 | A | Y | 10 |  | 014856 |  | 0 | N | ZGWC
1176 | 1037 | HUMS | 622 | Writing and Revision | JA1 | 2017-06-26 | 2017-08-01 | ..T.H.. 06:30PM-09:30PM |  | EMPLID | Instructor Name | 18 | 1 | A | Y | 10 |  | 014844 |  | 0 | N | ZGWC, ZONL
1176 | 1044 | HUMS | 644 | Incarceration and American Lit | JA1 | 2017-06-26 | 2017-08-01 | .M.W... 06:30PM-09:30PM |  | EMPLID | Instructor Name | 18 | 1 | A | Y | 10 |  | 014845 | C | 0 | N
1176 | 1045 | HUMS | 644W | Incarceration and American Lit | JA1 | 2017-06-26 | 2017-08-01 | .M.W... 06:30PM-09:30PM |  | EMPLID | Instructor Name | 3 | 0 | A | Y | 3 |  | 014845 | C | 0 | N | ZGWC
1176 | 1052 | HUMS | 654 | The Armchair Adventurer | JA1 | 2017-06-26 | 2017-08-01 | .M.W... 06:30PM-09:30PM |  | EMPLID | Instructor Name | 18 | 1 | A | Y | 10 |  | 014847 | C | 0 | N | ZONL
1176 | 1053 | HUMS | 654W | The Armchair Adventurer | JA1 | 2017-06-26 | 2017-08-01 | .M.W... 06:30PM-09:30PM |  | EMPLID | Instructor Name | 3 | 0 | A | Y | 3 |  | 014847 | C | 0 | N | ZGWC, ZONL
1176 | 1038 | MTHS | 619 | Linear Algebra | JA1 | 2017-06-26 | 2017-08-01 | ..T.H.. 09:00AM-12:00PM |  | EMPLID | Instructor Name | 18 | 0 | A | Y | 10 |  | 014849 |  | 0 | N | ZONL
1176 | 1055 | MTHS | 683 | Applied Data Analysis | JA4 | 2017-06-24 | 2017-07-02 | TBA |  | EMPLID | Instructor Name | 18 | 0 | A | Y | 10 |  | 014848 | C | 0 | N
1176 | 1039 | SCIE | 634 | Animal Reproduction | JN1 | 2017-06-19 | 2017-06-23 | .MTWHF. 09:00AM-05:00PM |  | EMPLID | Instructor Name | 18 | 0 | A | Y | 10 |  | 014850 |  | 0 | N
1176 | 1040 | SCIE | 635 | The Connecticut River | JA5 | 2017-08-07 | 2017-08-11 | .MTWHF. 09:00AM-05:00PM |  | EMPLID | Instructor Name | 14 | 0 | A | Y | 10 |  | 014851 |  | 0 | N
1176 | 1048 | SCIE | 682 | Adolescent Psychology | JA1 | 2017-06-26 | 2017-08-01 | .M.W... 06:30PM-09:30PM |  | EMPLID | Instructor Name | 18 | 0 | A | Y | 10 |  | 014852 | C | 0 | N | ZONL
1176 | 1049 | SCIE | 682W | Adolescent Psychology | JA1 | 2017-06-26 | 2017-08-01 | .M.W... 06:30PM-09:30PM |  | EMPLID | Instructor Name | 3 | 0 | A | Y | 3 |  | 014852 | C | 0 | N | ZGWC, ZONL
1176 | 1054 | SCIE | 683 | Applied Data Analysis | JA4 | 2017-06-24 | 2017-07-02 | TBA |  | EMPLID | Instructor Name | 18 | 0 | A | Y | 10 |  | 014848 | C | 0 | N
1176 | 1041 | SOCS | 632 | Between Marx and Coca-Cola | JA1 | 2017-06-26 | 2017-08-01 | .M.W... 06:30PM-09:30PM |  | EMPLID | Instructor Name | 18 | 0 | A | Y | 10 |  | 014853 |  | 0 | N | ZONL
1176 | 1042 | SOCS | 633 | Solving the World's Problems | JA1 | 2017-06-26 | 2017-08-01 | ..T.H.. 06:30PM-09:30PM |  | EMPLID | Instructor Name | 18 | 0 | A | Y | 10 |  | 014854 |  | 0 | N
1176 | 1046 | SOCS | 639 | History of Europe since 1945 | JA1 | 2017-06-26 | 2017-08-01 | .M.W... 09:00AM-12:00PM |  | EMPLID | Instructor Name | 18 | 0 | A | Y | 10 |  | 014855 | C | 0 | N | ZONL
1176 | 1047 | SOCS | 639W | History of Europe since 1945 | JA1 | 2017-06-26 | 2017-08-01 | .M.W... 09:00AM-12:00PM |  | EMPLID | Instructor Name | 3 | 0 | A | Y | 3 |  | 014855 | C | 0 | N | ZGWC, ZONL
1176 | 1050 | SOCS | 682 | Adolescent Psychology | JA1 | 2017-06-26 | 2017-08-01 | .M.W... 06:30PM-09:30PM |  | EMPLID | Instructor Name | 18 | 0 | A | Y | 10 |  | 014852 | C | 0 | N | ZONL
1176 | 1051 | SOCS | 682W | Adolescent Psychology | JA1 | 2017-06-26 | 2017-08-01 | .M.W... 06:30PM-09:30PM |  | EMPLID | Instructor Name | 3 | 0 | A | Y | 3 |  | 014852 | C | 0 | N | ZGWC
1176 | 1056 | SOCS | 683 | Applied Data Analysis | JA4 | 2017-06-24 | 2017-07-02 | TBA |  | EMPLID | Instructor Name | 18 | 0 | A | Y | 10 |  | 014848 | C | 0 | N